## Cover
BUG REPORT DOCUMENT
Indian Language Translator – QA Portfolio
Project | Indian Language Translator
Prepared By | Sambavi B
Tool | JIRA (Bug Tracking)
Total Bugs | 5
Critical | 0
High | 3
Medium | 2
Fixed | 3
Open | 2
Date | June 2025

## Bug Report
Bug ID | Title | Module | Severity | Priority | Status | Steps to Reproduce | Expected Result | Actual Result | Environment | Reported By | Date Reported | Fixed By | Remarks
BUG_001 | Same-language selection produces no warning | Language Selection | Medium | Medium | Fixed | 1. Set source to English 2. Set target to English 3. Click Translate | Warning: 'Source and target language cannot be same' | No warning displayed; same text returned as output | Windows 10, Python 3.11 | Sambavi B | 10-Jun-2025 | Dev Team | Fixed in v1.2 — validation added
BUG_002 | API returns HTTP 500 for unsupported language code | API | High | High | Fixed | 1. Open Postman 2. POST /translate with body: {text:'Hello', lang:'xx'} 3. Send | HTTP 400 Bad Request with error message 'Unsupported language' | HTTP 500 Internal Server Error returned — no error message | Postman, API v1.0 | Sambavi B | 11-Jun-2025 | Dev Team | Fixed in v1.3 — proper error handling added
BUG_003 | App becomes unresponsive after 8 rapid translation requests | Performance | High | High | Open | 1. Translate any text 2. Immediately click Translate 9 more times rapidly | All 10 translations complete without any crash or slowdown | App freezes on 8th request — requires force close | Windows 10, Python 3.11 | Sambavi B | 12-Jun-2025 | — | Open — reproducible 100% — assigned to backend team
BUG_004 | Telugu script shows minor glyph misalignment in output | Compatibility | Medium | Medium | Open | 1. Enter 'How are you' in English 2. Select Telugu as target 3. Translate 4. Inspect output text | Telugu script renders correctly with proper glyph spacing | Some Telugu characters appear with slight vertical misalignment | Windows 10, Arial Unicode font | Sambavi B | 13-Jun-2025 | — | Open — font rendering issue — low user impact
BUG_005 | Long paragraph (500+ chars) gets truncated during translation | Translation | High | High | Fixed | 1. Paste 500+ character paragraph into input 2. Select Tamil 3. Click Translate | Full paragraph translated completely without any character loss | Output truncated at approximately 490 characters — final sentences missing | Windows 10, Python 3.11 | Sambavi B | 14-Jun-2025 | Dev Team | Fixed in v1.4 — input character limit increased

## Bug Summary
BUG SUMMARY
Category | Count
Total Bugs Reported | 5
Critical | 0
High Severity | 3
Medium Severity | 2
Fixed | 3
Open | 2
Fix Rate | 60%
Tester | Sambavi B